## JRTC
ASG / INITAL SUPPORT BASE / LOGISTICAL SUPPORT BASE SYNCHRONIZATION MATRIX, AT-2001
PHASE I | [9 empty] | PHASE II ( as ESB crosses RP )
| 24 APR / D-21 | 25 APR / D-20 | 26 APR / D-19 | 27 APR / D-18 | 28 APR / D-17 | 29 APR / D-16 | 30 APR / D-15 | 01 MAY / D-14 | 02 MAY / D-13 | 03 MAY / D-12 | 04 MAY / D-11 | 05 MAY / D-10 | 06 MAY / D-9 | 07 MAY / D-8 | 08 MAY / D-7 | 09 MAY / D-6 | 10 MAY / D-5 | 11 MAY / D-4 | 12 MAY / D-3 | 13 MAY / D-2 | 14 MAY / D-1 | 15 MAY / D-DAY | 16 MAY / D+1 | 17 MAY / D+2 | 18 MAY / D+3 | 19 MAY / D+4 | 20 MAY / D+5 | 21 MAY / D+6 | 22 MAY / D+7 | 23 MAY / E-DAY | 24 MAY / E+1 | 25 MAY / E+2 | 26 MAY / E+3 | 27 MAY / E+4 | 28 MAY / E+5 | 30 MAY / E+7 | 31 MAY / E+8 | 01 JUN / E+9
| TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY
JRTC Command and Control (C2) | [8 empty] | ISB ADVON ARRIVES, Camp Gruber 10% Strength | ISB begins Setup |  | ISB MAIN BODY ARRIVES, Establish 232CSB Alt. TOC |  |  |  |  | ESB ADVON ARRIVES @ ISB, Advance Party for Heavy Team and LSA to Ft. Chaffee |  | ESB MAIN BODY ARRIVES / LSA MAIN BODY ARRIVES: ESB Light Team To ISB / ESB HVY Team to LSA | ESB LEAD ELEMENT DEPARTS LSA | Upscale OPS in LSA / Prep fpr CBT | ESB FULLY DEPLOYED into BOX via Wheel / Air | TOC Handoff from TF Lincholn to TF WillRogers, 345th Est Alt. TOC | ISB Closes | ISB Units Redeploy to H.S. | ISB CLOSES TRAINING, ORDANCE / SLINGLOAD OPS CONTINUE FROM ISB | RECOVERY OPERATIONS | LSA Closure Begins | LSA Closed | ESB DEPARTS BOX / Closeout | ESB REDEPLOY BEGINS, COMBAT OPS CONCLUDE | ESB REDEPLOYS | SITE RECOVERY OPERATIONS
KEY EVENTS | [8 empty] | 33D ASG signs for Camp Gruber | Handoff Camp Gruber from 33D ASG to 232CSB |  | Receive Equipment / Personnel | ISB Fully Operational |  |  |  | ESB Units occupy AA |  |  |  |  | ESB FULLY DEPLOYED into BOX via Wheel / Air | Complete Battle Handoff to LSA / LSA Assumes Full OPS | Deliver Push Package #2 |  |  | Final Push Package |  |  | JSTF Assumes Log Control
ISB (232nd) | [8 empty] | Initial Occupation | Assumes control of Camp Gruber from 33D ASG |  |  |  | Fully Operational |  |  | ESB Units occupy AA |  |  | Get ESB Combat Ready |  |  | Begin Recovery OPS | Closed for Business
LSA (345th) | [16 empty] | ESB Units occupy AA |  | Initial Occupation | Get ESB Combat Ready |  | 345th begins support mission to TF Thunderbird Pending RP | Complete Battle Handoff to LSA / LSA Assumes Full OPS | [5 empty] | Relocate to Recovery AA | JSTF Assumes Log Control
COMMO | [6 empty] | Draw FM from State |  | Unit Internal COMMO | Forward Directory Info to 33D ASG Commo section | Per SOI | [7 empty] | Establish MSE commo at LSA with Commercial Access to ISB |  |  |  |  | Turn-in SOI
Linehaual Opns (MIL/COM) | [21 empty] | As Required | As Required | Support Prep to Movement Home | [5 empty] | As Required
Air Operations | [11 empty] | Additional Buses for Airport Equipment / Personnel Handling | As Required | [8 empty] | Begins With Brigade movement and coordination with S-3(AIR)
Rail Operations | [10 empty] | Establish Rail Sites | Operate as Needed | Off Load as Required | [10 empty] | Support Prep to Movement Home
Barge Operations | [10 empty] | Recon Off Load sites | Operate as Needed | 33d ASG barge arrives for an offload | [14 empty] | Site Recon Prep. |  | Site Operations
Personnel / Admin. | [8 empty] | In Process thru Reception Center: BLDG 108 | Strength Report Due @ 0700 | Recon Off Load sites |  | Standard Reports as per OK SOP |  |  |  | LSA Personnel Inprocess @ Ft. Chaffee: Location to be determined | [5 empty] | All Reports to LSA ASG element
Class I | [8 empty] | begin Contracts Meals. Evening meal only for app. 10% for ISB personnel | Begin contract for all three meals advance parties. |  | 100% ISB personnel evening meal. Stockpile MRE's | 100% all three meals |  |  |  | Begins support @ LSA and increase support at ISB to support 345th deployment. Support 345th & TF Thunderbird |  | 100% Ration SPT @ ISB & LSA for 345th and TF Thunderbird | Shift Ration Request by Units | 232nd will Stage 3 day Ration Cycle for ESB | ISB Supports TF Thunderbird Breakfast. LSA 100% for duration |  |  |  | ISB Terminates Contract |  |  | Contracted Meals to Recovery AA | 100% Requirement for all Elements within Recovery of AA
Class II | Individual Unit Responsibliy
Class III / Class III (P) | [8 empty] | Credit Card Top Off |  | Identify /Prepare Bulk refueling Site at ISB | Conduct Retail Operations at ISB | [5 empty] | Est. Retail OPS @ LSA |  |  |  | Est. Wholesale to LSA |  | Terminate Retail @ ISB |  |  |  |  | Relocate Wholesale to Recovery AA
Class IV | [9 empty] | Establish AMMO Supply Point (ASP) |  |  | ASP fully operational |  |  |  | Coordinate Movement of Class IV |  | Pre-position as Required | [10 empty] | Prep. / Coord. Turn-in
Class V | [9 empty] | Sign for class V | [19 empty] | Prep. / Coord. Turn-in
Class VII
Class VIII (CHS) | [8 empty] | Provided by Post TMC
Class IX & Maintenance | [9 empty] | Unit REPS will sign for facilities. Coordinate with 232 CSB |  | 232 CSB has all 10 / 20 Maint. | DA 2406 Due |  |  |  | Available for ESB |  | Send Contact Teams to LSA |  |  |  | Contact TMs return to ISB/LSA is back-up | Terminate Maintenance | Coordinate support from ISB to LSA. |  |  |  |  | Unit DS Only
Billeting | [8 empty] | Sign for Facilities. Resident units will sign for block requirement |  | Begin Setup of Additional Billiting, Latrines, & Dumpsters |  |  | Ensure Fest Tent Erected |  |  | Coordinate with 232nd CSB for unit requirement | [5 empty] | Recover Fest Tents at ISB |  |  | Erect Temp Billiting at Recovery AA |  |  | Occupy Temp Billiting at Recovery AA | Occupy Temp Billiting at Recovery AA
Contracts | [8 empty] | Verify Meals |  | Verify Female Latrines / Tents | Verify Meal Increase |  | Verify billeting requirement met
TC Convoy Operations | [8 empty] | Limited from H.S. | Identify / Prepare Staging Areas | Ensure Trans Available for Arriving Units | As Required | Support Base Battle OPS Requirement | [8 empty] | 232 CSB Move units as required | Movement Order Turn-in |  | Coordinate Final Marching Orders |  |  |  | Convoy Clearance
PREPO FLEET OPNS
MP's | [9 empty] | Establish Movement Routes / Coordinate PMO | Area Recon | TCP / Route Marking | Law and Order Missions | [8 empty] | Conduct Force protection and law and order missions. |  | Hand-off Duty to PMO
RIGGING OPNS | [21 empty] | Commence OPS
MEDICAL | [8 empty] | TMC Operations
CONSOLIDATION POINT
WASH RACK OPNS | [11 empty] | Open for Business
SPO Operations | [8 empty] | Submit Closing Report, Sensitive items report |  | Begin ISB TOC Setup | Submit Closing Report and sensitive item report as Required |  |  |  |  | Submit Closing Reports |  | Est. Lsa TOC Directorte/ LOC |  |  | Track & Report Operations and Deployment | Hand-off TOC OPS from ISB to LSA | [6 empty] | Close Out SPO TOC / LOC
GSA VEHICLES | [6 empty] | GSA Vehicles Depart Chicago |  | Arrives Camp Gruber |  | Draw Additional GSA Buses