## Slide 1
GBS Industry Day
GBS Joint Program Office
SMC/MCB
LA AFB, CA
29 March 1996

## Slide 2
GBS Industry Day Agenda
0900 - Welcome CAPT Douglass
0915 - JPO Organization CDR Ayotte
0930 - System and Acquisition Overview LTC Howard
1010 Break
1020 - On-Going Related Activities LTC Howard
1050 - System Engineering LTC Howard
1100 - Broadcast Mgt Segment LTC Troxel
1130 - Terminal Segment LTC Ludwig
1200 - Summary CDR Ayotte
1215 Lunch
1330 - Questions/Answers

## Slide 3
Master Schedule
Transition Plan
Program Milestones
Phase I (Test Bed)
BC2A
BADD ACTD
Phase II (Interim)
Space - UFO/G Launch
Terminals
Uplink Sites &
Receive Equipment
Information Mgt (IM)
NGOC/TIM/SBM/RBM
Phase III (Target)
Space - Target
CY 1996 1997 1998 1999 2000
MR
Apr
PR
Jun
JWID 97
PII - IOC
Apr
PII - FOC
Mar
UFO 8
Jan
UFO 10
Jan
UFO 9
Aug
First
Jan ‘01
~ 3 year Build
Acquisition Process
Award
Specs
If DODSA directs to meet GBS requirements by ‘00
Specs
Solicitation
PM MILSATCOM
SMC
ESC
Award
Production
DEMO
Develop
Pilot
Evolve
Pilot
Phase I
Phase II
Phase III
OCONUS Pilot
Service
CONUS Pilot
Service
Final Operational
Service
Procurement Agency
Navy
Phase III
IOC 6/01
FOC 12/02
Award

## Slide 4
What We’re Looking For From You (RFI)
How you plan to participate in this effort from:
  Components to turn-key system
Technical approach
  Modified NDI leveraging off commercial technology
  Cost drivers
  Best way to satisfy our acquisition approach objectives
ROM costs
Responses due by COB 26 April 1996

## Slide 5
Where We Have Been
What is it that we want?
Are we serious?
Go buy it
OSD
Cost Performance Schedule
User’s
Integrated Product
GBS General Officer Steering Group
Services
OSD
YES!
USD(A&T) Direction
YES!
Endorsement
YES!
MNS
Cheap!!!
Set-top-box

## Slide 6
Where We Are Going
Users
Industry
Acquirers
Total Product to Customer
CINCs
Services
Intel

## Slide 7
What You Should Walk Away With
Integrated Team
On the “fast track” for delivery to market customer

## Slide 8
JPO Organization
CDR Ayotte

## Slide 9
GBS JPO
Individual Projects
Role of JPO
Integrated GBS Program

## Slide 10
GBS IPTs
SPACE
Lead: ESC/MC
Members: DISA CECOM ARPA SPAWAR NRO / OSO NSA AFC4A Labs SMC Other ESC
Users JTPO
TERMINALS
INFORMATION MANAGEMENT
EXTERNAL INTERFACES
SYSTEMS
INTEGRATION
Lead: SMC/MC
Members: DISA ESC
ARPA CECOM NSA SPAWAR Labs Users
Lead: PM MILSATCOM
Members: ESC SPAWAR SMC/MC NSA Labs Users
JTPO
Lead: Navy/UFO/G - Phase II
SMC/MC - Objective Phase III
Members: ESC CECOM
SPAWAR DISA NSA Labs
USSPACECOM
SMC/MC
Lead: SMC/MC
Members: DISA CECOM ESC AFC4A
ARPA SPAWAR NRO / OSO NSA Labs
XR
G
B
S
•
J
P
O

## Slide 11
GBS JPO Functional Organization
- Terminal planning & development
- Procurement of broadcast receivers
- Inter-service coordination
- Architecture Development/Support
- Requirements/CONOPS Support
- Spec’s ICD Development
- End-end Integration
- Info Broadcast Mgt Sys
- Interface into DISN
Director - SMC/MC
BG Kwiatkowski
Program Manager
CDR Ayotte (acting)
Systems Engineering
LTC Howard (USA)
Terminal Procurement
LTC Ludwig (USA)
Broadcast Management
Lt Col Troxel (USAF)
Washington Integration Office
CAPT Lee (USN)

## Slide 12
System and Acquisition Overview
LTC Howard

## Slide 13
Background - Why A GBS ??
Gulf War Experience
  First “Electronic / Information War”
US Information Transport Capacity Swamped
  Much Info Never Shipped To Theater Electronically
  Battle Maps Airlifted From CONUS Daily
Most Info Arriving In Theater Not Disseminated To Field
  Lacked Flexible Dissemination Systems
  Multi-Level Security Issues Never Solved

## Slide 14
Typical Theater Info Requirements
PC Modem
WWMCCS
56 Kbps
GCCS
512 Kbps
T1
1.544 Mbps
GBS
23 Mbps
ATO
1.1 Mbytes
Tomahawk
MDU
.03 Mbytes
Imagery
8x10
Annotated
24 Mbytes
DS TPFDD
250 Mbytes
1.02 hr
100 sec
22.2 hr
9.65 day
2.61 min
4.29 sec
57 min
9.92 hr
17.19 sec
.47 sec
6.25 min
1.09 hr
5.7 sec
.16 sec
2.07 min
21.59 min
.38 sec
.01 sec
8.4 sec
1.45 min

## Slide 15
GBS JPO Mission Statement
Near term objectives:
  Manage as an Integrated Product Team (IPT)
  Provide a GBS Testbed & Demo CONOPS
  Complete Program Review scheduled for July 96
  Execute Planning for the Interim GBS (GBS on UFO)
Provide warfighters with a worldwide, seamless,
high throughput broadcast information service
to support today's and tomorrow's missions.

## Slide 16
Technical Objectives
“To provide high data rate (in excess of 20MBPS per transponder) connectivity from CONUS to theater (or within and between theaters) to a distributed set of users through small aperture antennae and highly mobile terminals.”
“A GBS system is comprised of three basic elements - an information management segment, a broadcast segment, and user receive terminals.”
(DUSD-Space Report on the DoD Global Broadcast Service Program in response to the Department of Defense Appropriations Conference Report Jan, 1996)

## Slide 17
GBS Concept
NIMA
DIA
NRO
DMA
CIA
NSA
DARO
FNCC
GVC
CNN
AFRTS
“
“
“
UAV
JSTARS
JIC
JFACC
ELINT
AWACS
ABCCC
“
“
“
Broadcast
National
Sources
Theater
Deployed
Sources
IM & Injection
Receivers

## Slide 18
What Makes GBS Different
Pull
Pull
Information Management - Make GBS an Information Transport Service
Information
Management
Space
Segment
Terminal
Segment

## Slide 19
GBS Phased Implementation

## Slide 20
GBS Elements: Phase 1 (GBS Testbed)
SBM
Fixed
Inject Terminals
Fixed
Satellite
Phase 1
Ku Commercial
RBM
Fixed
End Users
DISA
NRO/OSO
AF
Army
Navy
Sources
Overall Systems Engineering & Integration and Program Management
Receive Terminals
Mobile
Smart Push
User Pull
Ku-based demo system

## Slide 21
Phase I Activities
Current Activities
  GBS CONOPS Testbed System
    2 transponders on lease - Ku band
    Commercial equipment being evaluated in operations
    USSPACECOM Regulating the GBS CONOPS Testbed System Usage
  DISA/ARPA/OSO/ESC Providing Bosnia Support
  ARPA Developing Battlefield Information Dissemination Concepts
  Army and AF Investigating Transportable Injection Concepts
Future Activities
  Develop overall acquisition strategy
  Ensure “Lessons Learned” from on-going activities get to Phase II/III Acq Mgrs

## Slide 22
Demonstration Schedule

## Slide 23
GBS Elements: Phase II (GBS Transponders on UFO)
SBM
Fixed
Mobile
Inject Terminals
Fixed
Mobile
Satellite
Phase 2
Ka on Navy UFO
RBM
Fixed
Mobile
Receive Terminals
Mobile
DISA
NRO/OSO
AF
Army
Navy
Sources
D I I
Overall Systems Engineering & Integration and Program Management
End
Users
D I I
Smart Push
User Pull
Other avenues
Secondary - Tactical Internet
Ka band system

## Slide 24
Phase II Activities
Current Activities
  Navy Planning to Procure UFO Hosted Space Segment
  Army Preparing for Inject Terminal Acquisition
  Army Preparing for Receive Terminal Acquisition
  Navy Examining Ship and Submarine Antenna Options
Future Activities - GBS JPO will integrate
  ESC’s management of Information Management Segment
  ESC’s coordination With DISA for GBS Integration to DII
  Army’s management of Receive Terminal Segment
  Army’s management of Inject Terminal Segment
  Navy’s management of Space Segment

## Slide 25
System Performance
Space Segment composed of four Ka-Band transponders
  3 Broadcast Beams
  UFO F8/F9/F10 Spacecraft
Each transponder will handle a data channel of 24 Mbps
  This channel can accommodate both High Speed Data and Compressed Video transmissions

## Slide 26
GBS Elements: Phase III (Target System)
Sources
SBM
Fixed
Mobile
Inject Terminals
Fixed
Mobile
Satellite
Phase 3
DODSA System
RBM
Fixed
Mobile
Receive Terminals
Mobile
DISA
NRO/OSO
AF
Army
Navy
D I I
End
User
D I I
Overall Systems Engineering & Integration and Program Management
Smart Push
User Pull
CONUS/Theater injection
Complete Information Mgm’t
Terminals used at sea, land, air
Objective System

## Slide 27
Phase III Activities
Current Activities
  DoD Space Architect Developing MILSATCOM Architecture Approaches for the Objective GBS
Future Activities
  JPO Will Manage Acquisition of Satellite, Terminal, and Information Management Segments
    If Space Segment Acquisition Needed (Per DODOSA), GBS JPO Will Lead Acquisition
    Army Will Lead Receive Terminal Acquisition
    Army Will Lead Inject Terminal Acquisition
    DISA Will Lead Information Management
    ESC Will Lead GBS Broadcast Management Acquisition
    ESC Will coordinate GBS Broadcast plug into DII socket

## Slide 28
Strawman WBS Structure and Format

## Slide 29
WBS Structure and Format (cont.)

## Slide 30
GBS Key Requirements
Requirements from MNS and CONOPS
  Use commercial equipment whenever possible
  UNCLASS through SCI
  Provide info to garrisoned, moving, and deployed forces
  Implement “Smart push” and “User pull”
  Support existing info dissemination requirements appropriate for one-way wideband transmission
  65N-65S worldwide service
  Compatible and integrated with existing/planned C4I systems
  Be compatible with existing/planned spacecraft control networks
  Provide for “lost” terminals
  Use non-proprietary interfaces

## Slide 31
  Support direct and theater injection
  Support peace through two MRCs (non-nuclear)
  Ability to route to all, subset, or single user group(s)
  Implement relevant DoD, national, and international policies, procedures, regulations, and restrictions for radio frequency spectrum management
  Allow IM to schedule/prioritize/deconflict transmission requirements
  Have all relevant interfaces between IM and data sources
  Allow IM to manage all incoming data
  Allow IM to coordinate all user requests
GBS Key Requirements (cont.)

## Slide 32
BREAK

## Slide 33
On-Going Activities Overview
LTC Howard

## Slide 34
BADD
DDS
IBS
Satellite
Broadcast
Management
GBS Related Activities
DoD Information Management
System
National or Theater
Information
Management
Other Media
Receive
Broadcast
Management
GBS JPO
C2 Systems
User Pull
DISA
DISN
Cmcl SatCom
Bosnia
Command & Control Augmentation
(BC2A)
Battlefield Awareness and Data Dissemination (BADD)
Defense Dissemination Service (DDS)
Integrated Broadcast Service (IBS)
UFO Packages
System Security
Information
Sources
GBS

## Slide 35
Bosnia Command/Control Augmentation (BC2A)
BOCA OBJECTIVES
VSAT - Secure Tactical Internet - MAPS and VTC
ARPA Lead - DISA/NRO Support ORION satellite - 3 transponders
Ground Segment
  12 Command Control Centers
  Predator unmanned aerial vehicle
  Proven - Common Operating Picture (COP)
BENEFITS TO GBS
BOCA will provide operational experience to refine the CONOPS for follow-on GBS phases
BOCA POC:
Col Forbes
GBS JPO Interface:
Maj Scearse
DIA
NPIC
NSA
Theater GCCS Operations Center
OPS/Intel
Support Center
Theater Bcast
Mgmt Center
DBS
VSAT DISN
(SIPRNET)
DBS
Broadcast
Center
National GCCS Operations Center
JCS Operations
Information Server
DMA
CC
DISN (SIPRNET)
CC
CC
CC
Deployed
Node
DISN (SIPRNET)
SOCOM
CENTCOM
ACOM
MGS
DISN (SIPRNET)
Internet
CNN
GWx
OCONUS LINK
• • •
JAC
Rear Echelon
Node
VSAT
DBS
GCCS
GCCS-LES
Imagery
Server
Information
Server
Open Sources
• Deployed
• NATO
Other CINCs
& Operations
Other
Sources

## Slide 36
Bosnia C2 Augmentation System
DIA
NPIC
NSA
Theater GCCS Operations Center
OPS/Intel
Support Center
Theater Bcast
Mgmt Center
DBS
VSAT DISN
(SIPRNET)
DBS
Broadcast
Center
National GCCS Operations Center
JCS Operations
Information Server
Military Information Sources
DMA
CC
DISN (SIPRNET)
CC
CC
CC
Deployed
Node
DISN (SIPRNET)
SOCOM
CENTCOM
ACOM
Operations
MGS
DISN (SIPRNET)
Internet
CNN
GWx
OCONUS LINK
• • •
JAC
Rear Echelon
Node
VSAT
DBS
GCCS
GCCS-LES
Imagery
Server
Information
Server
Open Sources
• Deployed
• NATO
Other CINCs
& Operations
Other
Sources

## Slide 37
Master Program Schedule (1 of 2)
I
Phase 0
II
Tasks
Jan
Feb
Mar
Apr
May
ATP (23 Jan)
15-24 Apr
25 Apr
TBD pending
EUCOM decision
EUCOM 17-21 Mar
8-13 Apr
Deployment
Site Surveys
CONUS Test
Ship/Install initial EUCOM Sites
Initial Sites IOC
Additional Sites
Communications
Transponders & Landing Rights
VSAT Procurement & Integration
JBS Rcvr Procurement & Integration
Predator site surveys, shipping, install
Predator Communications test
Deployed node integration
Broadcast Management Center
Integration with JWICS
Add JBS Receive Sites
Information Management
Info Mgmt CONOPS & manning concept
Information Management Architecture
Applications Procurement &Integration
Information Security Architecture
Initial Web Management capability
Initial Broadcast Mgmt capability
Common Operational Picture
Fixed Node integration
Deployed node integration
Deployed / Fixed Node
Information Server Procure. & Int.
VSAT and JBS Comms subsystems
Integration with GCCS / JMCIS
IPA Integration with JDISS
Integration & Delivery
Joint InfoMgmt Cell
Theater InfoMgmt Cell
Intelsat 602
16 Jan
Landing Rights
16 Feb
T3
24 Feb
ORION 14
29 Feb
28 Mar
VSAT 15 Mar
VSAT IOC 15 Mar
28 Mar
7 Apr
BMC2 28 Mar
Procurement 23 Feb
7 Apr
CONUS Demo
1 Apr
CONUS Demo
14-23 Feb
IOC 29 Feb
7x24 Ops
7 Apr
TBD
Sites 1-5
7 Apr
Sites 6-8
25 Apr
JBS 7 Apr
CONUS Demo Sites29 Feb 7Mar
Draft
23 Feb
Update & App.
13 Mar
Update
TBD
TBD
7 Apr
Ship #1-5 1 Mar
CONOPS 1 May
28 Mar
SW Delivered 27 Feb
Packet Testing
8 Apr
IOC 29 Feb
28 Mar
CONUS Sites 1-3 1 Apr
EUCOM Sites 1-4 15 Apr
TBD
TBD
TBD
28 Mar
29 Feb
13 Mar
CDR 18 Mar
CDR 18 Mar
SW Delivery TBD
JBS 18-24 Mar
Final
1 Apr
EUCOM Conf
15 Apr
Equipment 15 Mar
Initial Th. CONOPS 8 Mar
CONUS Test
1 Apr
IOC
25 Apr
Crypto
Tunnel
10 May
NATO
1 June
IOC 25 April

## Slide 38
I
Phase 0
II
Tasks
Jan
Feb
Mar
Apr
May
Deployment Milestones
Mission Support Products and Applications
DIA Support
CIA Support
NSA support
Imagery and targeting support
DMA mapping support
In-theater tailored map products
Weather support
Collaboration
Security
Architecture
Documentation/Accreditation
Encryption Devices/Keying Materials
ILS
CONOPS Annex
ILSP
Depot/Distribution Center
On-site Support
User Documentation
Test
Test Objectives
Test Scenario / Script
Test Plan
Test Procedures
Functional Tests/Checks
CONOPS
Main
Annexes
CONUS Test
8-13 Apr
25 Apr
1st Draft 18 Mar
25 Apr
25 Apr
25 Apr
25 Apr
25 Apr
25 Apr
VTC 25 Apr
Advanced
TBD
TBD
TBD
TBD
FBIS 3 Apr
NPIC 22 Mar
IOC 8 Mar
Vers.1 1 Mar
VTC IOC 15 Mar
IOC 8 Mar
Draft 15 Apr
Critical Issues Review
13 Mar
Checklists 29 Mar
1 - 7 Apr
Final 29 Mar
Final 22 Mar
Final 29 Mar
Draft 22 Mar
Final Draft 22 Mar
15 Apr
15 Apr
Baseline 13 Mar
8 Mar
CDR 18 Mar
Interim 1 Apr
Interim 1 Apr
Draft 22 Feb
Final 25 Apr
2nd Draft 12 Apr
Final 25 Apr
1st Draft
18 Mar
2nd Draft
27 Mar
Final 10 Apr
Draft 15 Feb
Draft 12 Mar
Final
22 Mar
A
4 Mar
D
15 Feb
B<C
4 Mar
G,H
22 Mar
E,F
29 Mar
Master Program Schedule (2 of 2)

## Slide 39
Battlefield Awareness and Data Dissemination (BADD)
BADD OBJECTIVES
Allow commander to tailor own info system
Place info dissemination capability in field
Provide tools to dynamically reconfigure displays
Provide access to multiple types of info
Deliver consistent battlefield picture; integrate tactical, operational, and national multimedia information
Allow warriors to manipulate, visualize, and apply information to tactical/strategic situations
Push (broadcast) and Pull (request) system
BENEFITS TO GBS
Develop IM concept of “Intelligent Push” via Info Dissemination Service (IDS)
Develop User IM tool concept “Warfighter Associate”
  Intelligently assist users to filter, user, and store GBS data
Pathfinder to test using Joint Tactical Internet for “User Pull”
Employ and test use of ATM for IM
BADD POC:
Bob Douglass
GBS JPO Interface:
Lt Col Howard

## Slide 40
Battlefield Awareness and Data Dissemination (BADD)
• Manage, store, disseminate, search, retrieve, edit, and integrate information (distributed)
• Information anchor desk
- Digest
- Summarize
- Publish
Information
Dissemination
Servers (IDS’s)
Information
Sources
National
Intelligence
Assets
UAVs
Tactical
Reconnaissance
Aircraft
Exploitation/
Fusion Nodes
Operational
Units
All
Source
Centers
•
•
•
Weather
Units
Information
Source
Repositories
National
Intelligence
Repositories
Tactical
Intelligence
Repositories
Operational
Repositories
Fused Information
Repositories
Global
Broadcast
Service
• High bandwidth one-way broadcast based on low-cost commercial receiver equipment
• All data tagged with source, time, location, quality, etc.
• Low to medium bandwidth tactical two-way communications based on integration of ATM, IP (Internet), and legacy protocols
Warfighter’s
Associates (WFA’s)
Uplink
Managers
Reachback
Tactical
Comms
UAV
• Receive, filter, store locally, search, browse,
profile prefetch, remote query, integrate, exploit, and visualize information
Exploitation/
Fusion Nodes
Operational
Units
Located at:
Tactical Systems/Nodes
- ASAS - MCS/P
- IAS - TCO
- JMCIS

## Slide 41
BADD Schedule
OCONUS Pilot Service
Focus on Joint Operations
IDS node OCONUS
OCONUS WFA’s
Information anchor desk
Leased GBS comm. satellite OCONUS
Additional tactical comms.
Advanced fusion (GOB, MOB)
Initial fusion manager
Integrated view of battlefield (includes NOB, AOB)
Additional applications (e.g., joint fires coordination)
Additional GCCS LES
applications
User defined requirements
Focus on Enhanced Capability
Enhanced IDS and WFA
Fusion manager
Integrated applications database and common query language
Additional applications
User defined requirements
Final Operational Service
Residuals
Demos
Development
Initial Capability
to 2 AD & USMC
Task Force XXI
OCONUS
Exercise
UAV Broadcast
Phase I
Phase II
Phase III
CONUS Pilot Service
Focus on Joint Maneuver Forces
IDS node at AHPCA
USACOM IPA
Multiple WFA’s
Leased GBS comm. satellite
Fused enemy/friendly picture
for GOB
Integrated viewer of image,
video, SIGINT, terrain, and
GCCS and MCS operational
data
3-D terrain/image mission rehearsal
SAIP SAR exploitation
User defined requirements
Joint Demo
Primary Demos
Secondary Demos
FY96
FY97
FY98
FY99
FY00
CONUS
Exercise

## Slide 42
Defense Dissemination Service (DDS)
DDS OBJECTIVES
Sends digital imagery to SIOP tasked U&S commands & multiservice tactical users
Processing segment accepts imagery data, compresses it, sorts it on a user basis, encrypts its, and transmits it via ...
Transmission segment - Relays imagery and process control data over terrestrial and satellite (DSCS and COMSAT) communications
Receive segment expands the compressed imagery, archives it, records it on film, sends it to a softcopy system
BENEFITS TO GBS
DDS will:
  Serve as a pathfinder for IM and BM services
  Packages large data files
  Handles big number of large data files that come in “bursts”
  Provides archive and retrieval for “user pull”
DDS POC:
Capt Fyfe
GBS JPO Interface:
Lt Col Howard

## Slide 43
DDS Mission
PMD 5005 (15) Apr 94, “DDS is an operational program which disseminates near-original quality digital imagery to the SIOP tasked U&S commands and multiservice vice tactical users in near real time.”
Defense Dissemination Program Office will:
  Develop, acquire, operationally support, and maintain the Defense Dissemination System
  Conduct follow-on system studies and technology efforts

## Slide 44
Defense Dissemination Service (DDS)

## Slide 45
Integrated Broadcast Service
IBS OBJECTIVES
IBS is the migration of the TDDS, TIBS, and TRIXS Intelligence Broadcasts to a single system of systems that envisions using GBS when appropriate in the long term for its high data rate transmissions and UHF for its low data rate transmissions
BENEFITS TO GBS
Serve as pathfinder for Broadcast Management services
  Consolidating inputs to one output data stream
  Packaging (or re-packaging) data to common format
  Prioritizing data to go on broadcast
Be integrated into DII (like GBS)
Implement “user pull” capability
Eventually transition (~2000) from UHF broadcast to GBS
IBS POC:
LCDR Johnston
GBS JPO Interface:
Lt Col Howard
Global/Theater
Theater/Global
(JTIDS, OTCIXS, TIBS, and OTHER)
Corps / MEF
Theater Networks
TRIXS
TDDS and
TADIXS-B
UHF
UHF
TIBS
17

## Slide 46
IBS Mission
The mission of an Integrated Broadcast Service is to resolve the uncoordinated proliferation of “stovepiped” intelligence broadcasts by providing the tactical commander with integrated time-sensitive tactical information
Manage the integration of several intelligence broadcasts into a system of systems, and migrating tactical terminals and receivers into a single related Joint Tactical Terminal (JTT) family

## Slide 47
Current Intelligence Broadcast Systems
Global/Theater
Theater/Global
(JTIDS, OTCIXS, TIBS, and OTHER)
Corps / MEF
Theater Networks
TRIXS
Although TRAP, TIBS, and TRIXS UHF broadcasts support the NRT needs of global, theater, and local users, they are hindered by a lack of interoperability, commonality and standardization.
TDDS and
TADIXS-B
UHF
UHF
TIBS

## Slide 48
Broadcast Integration to 2000+
BROADCAST INTEGRATION TO 2000+
Broadcast
Two-Way
Non-GBS
SATCOM
Current (FY96-97)
Low Data Rate
Interactive
GBS
LOS
Networks
D a t a F e e d
Data
Feed
Data
Feed
Data
Feed
Data
Feed
MTN
TDDS
BINOCULAR
TIBS
TRIXS
High Data
Rate
LOS
Transition
(FY98-99)
Objective (FY00+)
DII
IBS
“System of
Systems”
DII

## Slide 49
Philosophy for Broadcast Migration
The IBS should meet the NRT requirements for global, theater and local users. Specifically, it should:
  Provide data in a common formatted message
  Be medium-independent - utilize any appropriate portion of the Defense Information Infrastructure (DII)
  Be compatible with existing UHF migration receivers (MATT and CTT) when retrofitted with Common IBS modules
  Take advantage of emerging high data rate comm paths (e.g. - GBS)
  Be adaptable to other technological advances
  Be responsive to user queries and verification requests

## Slide 50
IBS on GBS Concept of Operations
Information Providers
User Pull
Request
Integrated Broadcast Service (IBS)
National Imagery (CIO)
Theater Data (CINC)
Air Tasking Order (JFACC)
Fleet Broadcast (Navy)
JDISS Products (multi-source)
Weather Reporting (multi-source)
Tomahawk Mission Data (Navy)
Situation Awareness (Services)
Logistics (Services)
Training (Services)
AFRTS
TVRO, CNN, Movies
DISN
Theater Injection
Primary Injection
User Pull
Requests
Broadcast Management Center

## Slide 51
IBS Milestones
NEAR TERM
1996-97
TIBBS Common Data Transfer
  Streamlined TIBS to TDDS data conversion
Channel Sharing (TBD)
Increased inter-operation
  Guardrail to be a TIBS producer/user
  Joint policy/operations
  Gateways
MTN Introduction
JTT interim terminals
Study/assess JTT applicable
technology
Broadcasts
Tactical
Terminals
MID TERM
1998-99
Common TDDS/TIBS/TRIXS
format
  TADIL-J
MTN network management
integrated with TDDS
Implementation of BINOCULAR concepts
TDDS/TIBS cooperative data management for optimum UHF bandwidth use
Common IBS Modules (CIBS-M)
  JTT family migration
Broadcasts
Tactical
Terminals
FAR TERM
2000+
Portions of UHF broadcast transitioned to GBS and other common assets
Increased leverage off commercial technology and products
Broadcasts and interactive networks integrated into DoD Communications Infrastructure
Increased leverage off commercial technology and products
Broadcasts
Tactical
Terminals

## Slide 52
System Engineering
Lt Col Howard

## Slide 53
GBS JPO Functional Organization
- Terminal planning & development
- Procurement of broadcast receivers
- Inter-service coordination
- Architecture Development/Support
- Requirements/CONOPS Support
- Spec’s ICD Development
- End-end Integration
- Info Broadcast Mgt Sys
- Interface into DISN
Director - SMC/MC
BG Kwiatkowski
Program Manager
CDR Ayotte (acting)
Systems Engineering
LTC Howard (USA)
Terminal Procurement
LTC Ludwig (USA)
Broadcast Management
Lt Col Troxel (USAF)
Washington Integration Office
CAPT Lee (USN)

## Slide 54
GBS JPO Systems Engineering
SE&I activities currently focused on integrating legacy
efforts with new concept and architecture development
  Frequency management & applications
  Constellation effectiveness & placement
  Communications link budgets
  Downlink availability and responsiveness
  Throughput traffic modeling

## Slide 55
Frequency Management Groundrule
All bands considered in original GBS system definition
X and Ka bands investigated in depth for Oversight Committee
  Ka band recommended
GOSC, JROC endorsed recommendation
GBS JPO position:
  Contractors may suggest other than Ka band,
but must address:
    Foreign coordination issues
    Interference to/from MILSATCOM and other military
and National systems

## Slide 56
Communication Link Budget Groundrule
Standard link budget format developed and available
GBS JPO Position:
- Contractors may use own budget formats, but
must reconcile those with GBS JPO provided
standard

## Slide 57
Downlink Availability
Global Rain/Atmosphere Availability model
developed (GLIMPSE)
Inputs:
  Satellite locations
  Frequency
  Margin availability against rain, atmospheric
  Loss at reference geometry
Uses coordinated Crane model to calculate average
annual availability
GBS JPO Position:
  Contractors provide comm link margin against rain/
atmospheric loss at reference geometry - GBS JPO
will assess using GLIMPSE

## Slide 58
Broadcast Management Segment
Lt Col Troxel

## Slide 59
GBS JPO Functional Organization
- Terminal planning & development
- Procurement of broadcast receivers
- Inter-service coordination
- Architecture Development/Support
- Requirements/CONOPS Support
- Spec’s ICD Development
- End-end Integration
- Info Broadcast Mgt Sys
- Interface into DISN
Director - SMC/MC
BG Kwiatkowski
Program Manager
CDR Ayotte (acting)
Systems Engineering
LTC Howard (USA)
Terminal Procurement
LTC Ludwig (USA)
Broadcast Management
Lt Col Troxel (USAF)
Washington Integration Office
CAPT Lee (USN)

## Slide 60
What We Need From You
Innovative and Cost Effective Solutions That Meet the DOD’s Global Broadcast Service Needs
Technical Solutions That:
  Maximize the Use of Commercial Off The Shelf (COTS) and Non-Developmental Items (NDI)
  Build Upon / Draw From Capabilities Developed as Part of Other GBS Related Activities (BC2A, BADD, etc.)
  Use Open Standards That Permit Flexibility & Future Growth
Novel Acquisition and Development Approaches That Meet Schedule Constraints
  JWID 97 Demo - Summer 1997
  GBS Phase 2 IOC - April 1998

## Slide 61
GBS Broadcast Management
Intel
Logistics
Medical
Weather
Admin
MC&G
Open Source News
Broadcast
Management
CONUS
IN-THEATER
Broadcast
Management
UAV
BDA
Joint
Stars
OPS
TR1

## Slide 62
GBS BM Within the DISN / DII
Information
Sources
Information
Sources
Information
Sources
Information
Sources
DoD Information Delivery Management
TIM
Other Media
GBS
GBS BM
GBS
DoD IM
C2 Systems
User Pull
Missed
Messages
SBM
RBM

## Slide 63
Notional GBS (Phase II)
DISN / DII
User Pull (Any Available Media)
UFO/G
SBM
Injector
National Sources
TIM
RBM
In-Theater Injector
SBM
Theater Sources
TIM
End Users
Receiver
Satellite Control Facility
Deployable Comm Infrastructure

## Slide 64
GBS Theater IM (TIM)
DISN / DII
User Pull (Any Available Media)
UFO/G
SBM
Injector
National Sources
RBM
In-Theater Injector
Theater Sources
End Users
Receiver
Satellite Control Facility
Deployable Comm Infrastructure
TIM
SBM
TIM
Functions:
Aggregate CINC Information Requirements
Manage CINC Broadcast Schedules / Prioritization
Maintain CINC Resource Allocations Within JCS Apportionment
Provide SBM Status Feedback to CINCs / End Users
Archiving
Interfaces:
DISN / DII
Information / Data Sources
Satellite Broadcast Manager (SBM)
CINCs / Command Centers

## Slide 65
GBS Satellite Broadcast Manager (SBM)
DISN / DII
User Pull (Any Available Media)
UFO/G
Injector
National Sources
TIM
RBM
In-Theater Injector
Theater Sources
TIM
End Users
Receiver
Satellite Control Facility
Deployable Comm Infrastructure
SBM
TIM
Functions:
Assemble Uplink Data Stream
Broadcast Schedule / Program Guide
Transmission / Retransmission / Error Handling
Process User Requests (Pull, “Missed” Files, etc.)
Payload Control / Antenna Beam Pointing
Queuing / Archiving
Crypto / Rekey / Terminal Compromise Recovery
Interfaces:
DISN / DII
Information / Data Sources
Theater Information Manager (TIM)
Injector Terminals
Satellite Mission Control System
SBM

## Slide 66
GBS Receive Broadcast Manager
DISN / DII
User Pull (Any Available Media)
UFO/G
SBM
Injector
National Sources
TIM
In-Theater Injector
SBM
Theater Sources
End Users
Receiver
Satellite Control Facility
Deployable Comm Infrastructure
SBM
TIM
RBM
Functions:
Process Downlink “Bit Stream”
Filter Information Per CINC / End User Profiles
Disseminate Information to CINCs / End Users
Process User Queries (Pull, Retransmission, Rekey, etc.)
Display Program Guide
Identify “Missed” Files (SBM Transmit vs. RBM Receive Record)
Archiving
Interfaces:
Receiver Terminals
CINCs / End Users
Deployable Communications Infrastructure (e.g., TASDAC, MSE)
DISN / DII

## Slide 67
Summary
GBS Broadcast Management is on a Fast Track to Deliver an Operational Capability in Early 1998
The Government Needs Industry’s Help to Define Innovative Acquisition Approaches and Cost Effective Technical Solutions for GBS Broadcast Management
We Welcome Your Inputs and Ideas

## Slide 68
Terminal Segment
LTC Ludwig

## Slide 69
- Terminal planning & development
- Procurement of broadcast receivers
- Inter-service coordination
- Architecture Development/Support
- Requirements/CONOPS Support
- Spec’s ICD Development
- End-end Integration
- Info Broadcast Mgt Sys
- Interface into DISN
Director - SMC/MC
BG Kwiatkowski
Program Manager
CDR Ayotte (acting)
Systems Engineering
LTC Howard (USA)
Terminal Procurement
LTC Ludwig (USA)
Broadcast Management
Lt Col Troxel (USAF)
Washington Integration Office
CAPT Lee (USN)
GBS JPO Functional Organization

## Slide 70
Terminal IPT Point of Contact
Army-Future PM MILSATCOM
  LTC Ludwig/Eric Davis
GBS Joint Program Office-LTC Craig Howard
AF/ESC-Kathy Turbridy
Navy-Bernard Kohn
JTPO-Jerry Ingerski
Signal School-CPT Sizemore

## Slide 71
Terminal GBS IPT
TERMINAL ENG. IPT FACILITATOR ERIC DAVIS
PM TACTICAL TERMINALS
LTC DAVID LUDWIG
TBD
LOG.
AIR FORCE TERMINAL INTEGRATION
PROGRAM BUDGET/ACQ
PROCUREMENT
COST EST.
NAVY TERMINAL INTEGRATION
INFORM. MGMT.
S&TCD
TERMINAL REQTS
SIGCEN CPT SIZEMORE
LEO WALTSAK
FAITH TEITELBAUM
JACKIE SAYNE
EMERSON KESLAR
LNO
LNO
CONTRACTING
LARRY ASCH CPT LYNN KINLEY
SYSTEM ENG.

## Slide 72
GBS Terminal Segment
Terminal Segment includes
  Injection Terminals
    Strategic-Fixed Site
    Tactical-Mobile Site
  Receive Terminals
    Transportable
    Airborne
    Shipborne
Army is the Terminal Acquisition Lead

## Slide 73
Phase II Terminal Definition Strawman
UFO
BASED
SPACE
SEGMENT
UC
MOD/ CODER
*ENCRYPT
UC
MOD/ CODER
*ENCRYPT
UP TO
FOUR
INJECTION TERMINAL
1.5 TO 23.5 Mbps
INFORMATION MANAGEMENT RESPONSIBILITY
RECEIVE TERMINAL
SVGA
TBD
NTSC
ATM
IP
TRACKING
ANTENNA
HPA
RF Mux
ANTENNA
TRACKING
LNB
IRD
*DECRYPT
* EXACT LOCATION OF BULK ENCRYPTION IS TBD

## Slide 74
Terminal Industry 1-1 Sessions
Commerce Business Daily Announcement-20 Feb
Market Analysis of Projected GBS Terminal Capabilities
Projected Terminal Capabilities Published on CECOM Electronic Bulletin Board (EBB) 11 Mar
Solicit Industry Ideas on Terminal Capability Feasibility During 20-21 Mar Industry one-on-one sessions at Ft. Monmouth
POC is CPT Lynn Kinley, (908) 532-5489

## Slide 75
Market Analysis Assumptions
Modified Non Developmental Item (NDI) Strategy- Not True Commercial Off The Shelf (COTS)
Terminals Needed to support Sep 97 UFO 8 GBS Satellite Payload Ground Testing
Approved Joint Operational Requirement Document (JORD) by Jul 96
Phased Approach to Objective Terminals

## Slide 76
Projected GBS Terminal Schedule
TERMINAL IPT FORMED
JORD DEVELOPMENT
JPO INDUSTRY DAY
MARKET SURVEY ANAL
TERMINAL 1-ON-1’s
ACQUISITION STRATEGY
DRAFT DOCUMENTS (EBB)
ISSUE SOLICITATION
AWARD/PRODUCTION
TRANS/REC DEMO
UFO/GBS LAUNCH
SYSTEM TEST DT & OT
J F M A M J J A S O N D J F M A M J J A S O N D J F M A
TASK
1/5
2/27
1/97
9/29
11/28
12/23
8/15
4/30
8/1
3/22 4/27
3/21
3/22
3/11 4/12
3/27
3/7
6/15
7/1
1/16
FY96
FY97
FY98
7/11

## Slide 77
Conclusions
GBS Terminal IPT Welcomes Industry Ideas to Develop a Sensible, Cost Effective, COTS/NDI-based GBS Terminal Program That Will Meet User Needs
Plan To Incorporate Industry Comments In All Terminal Procurement Documentation

## Slide 78
Summary
CDR Ayotte

## Slide 79
Acquisition Philosophy
Leverage Commercial Products
  Key driver for delivering system within budget
Partnership with Industry
  Must evolve system approach with commercial infrastructure
  Allow for possible multiple contracts
Team Approach and Agency Partnerships
  Capitalizing on team strengths - remove parochial boundaries
Target on Mid/Long Range GBS Solution
  Maximizing capability to cost - knee of curve - good enough
Innovative Acquisition Approaches
  Open architectures to maximize competition

## Slide 80
Summary - What Needs To Be Done...
Program Review
6 Aug
Define System Components
FEB MAR APR MAY JUN JUL AUG
Allocate Responsibilities
Develop System/Program Cost
Partnership with Industry
Develop Acquisition Strategy
Draft Program Review Package
Principals Mgt & PR Review
OIPT Review
OIPT Review
Principals Strategy Meeting (held 2/6)
Principals JPO Mgt Review
Formal JPO Kick-off Meeting (no longer needed)
Tasks
Events
GBS
Team
JPO
Management
Structure
Review
Space Architect
MILSATCOM
Architecture
Objective
GBS
System
Requirements Definition ... in process
today
.... OSD Direction ..............?
Oct
95
Draft package briefed to AQSS
Draft out to AO for review

## Slide 81
What We’re Looking For From You (RFI)
How you plan to contribute to this effort:
  From components to turn-key system
Technical approach
  Modified NDI leveraging off commercial technology
  Cost drivers
  Best way to satisfy our acquisition approach objectives
ROM costs
Responses due by COB 26 April 1996

## Slide 82
QUESTIONS???