Administrator’s Weekly Report

Economy

May 15 -May 21, 2004

HIGHLIGHTS

- A Ministry of Trade delegation attended the World Trade Organization General Council meeting May 17–18, 2004 in Geneva Switzerland.  This was the first formal participation in the WTO by Iraq since receiving its observer status earlier this year.

- The first microfinance loan has been made in Falluja -- $1,500 to an auditor to buy a car for business travel.

- As of May 21, 2004, estimated crude oil export revenue reached $6.2 billion for 2004 (crude oil export revenue for 2003 [June - December] was $5.1 billion).

I.  BUILD FINANCIAL MARKET STRUCTURES

Modernize the Central Bank; 	Commercial Banking System; Re-establish Baghdad Stock Exchange; Restructure National Debt

- Renovations of the Iraq Stock Exchange temporary site are complete, and interim regulations have been drafted.  Staff members are preparing contracts between the Depository and the brokers and listed companies in support of the dematerialization process, by which investors hand in their paper certificates for verification by the listed company, and deposit into the Depository.  Employee training is also underway.

- At the New Iraqi Dinar (NID) auction on May 20, the settlement price was 1,465 dinars per dollar, the same as the previous day, and unchanged from a week ago.  The amount of dollars sold at the auction varied over the week from $0.6 - $18.7 million.

- New Iraqi Dinar monthly fluctuation:

  - February 20 – March 20: 			NID depreciated    0.4 percent

  - March 20 – April 20:	 			NID depreciated    2.5 percent

  - April 20 – May 20:	 			NID depreciated    0.7 percent

Source:  CPA Senior Advisor to the Central Bank of Iraq

- The annualized weekly volatility of the New Iraqi Dinar this past week was 1.6 percent.

- The consumer price index (CPI) is computed and published monthly by the Central Statistical Office (CSO). The April CPI declined by 3.7 percent relative to its level in March, partially reversing the 9.2 percent increase in March.  The decline was broad based (see chart below).  The large increase in March was dominated by that fact that rents are only measured every six months and are reflected fully in the index only in those months.  In addition, monthly inflation data have a distinct seasonal pattern, with seasonally low rates in the late spring and summer, but the index prepared by the CSO is not yet available in a seasonally adjusted version.

- As measured by the CPA, the April 2004 annualized inflation rate was 19.6%, down from its peak of 47.7% in October 2003. Over the past six months the CPI has risen by 3.5 percent or by 7.0 percent at an annual rate. The CPI has been virtually unchanged on balance since the beginning of the year.

Source:  CPA Senior Monetary Policy Adviser to the Central Bank of Iraq;

Central Statistical Office

II.  DEVELOP TRANSPARENT BUDGETING AND ACCOUNTING ARRANGEMENTS

Redrafting and Execution of 2004 Budget

- On May 16, CPA Administrator L. Paul Bremer signed CPA Order Number 87, Public Contracts Law, which promulgates a law for public procurement in Iraq.  The Order provides, to the maximum extent practicable, for full, fair and open competitive public contracting procedures.  The Order instills the principles of transparency, predictability, fairness and equality of treatment in the Iraqi procurement process.  The Order is designed to bring Iraqi procurement procedures into accordance with internationally-recognized public procurement standards.

- As of May 20, the balance in the Development Fund for Iraq (DFI) was $10.2 billion, comprised of $8.4 billion in the original Federal Reserve Bank of New York (FRBNY) account, and $1.8 billion on deposit in DFI-Baghdad.  Of this, $3.1 billion is already committed to projects, and the remaining $7.1 billion is slated for projected 2004 budget items.  Since establishment, the DFI investment program at FRBNY earned $24.9 million in interest.  As of May 20, the total payments out of the DFI amounted to $8.7 billion.

- The Program Management Office (PMO) intends to commit $10.4 billion (56 percent of the $18.4 billion supplemental) toward contracts by July 1, 2004.  As of May 18, $7.4 billion are committed to Iraq relief and reconstruction efforts, 71 percent of the July 1 goal.  As of May 11, $4.2 billion of funds are obligated with contractors (40 percent of the committed fund’s goal).  The following shows the money committed by sector as of May 18 against the July 1 target.

Source: Program Management Office

- Section 2207 of the Emergency Supplemental Appropriations Act for Defense and for the Reconstruction of Iraq and Afghanistan, FY 2004 (Public Law 108-106) enumerates the allotments granted to CPA for each sector and levies a quarterly reporting requirement to Congress detailing PMO’s spending.

III.  DESIGN OIL TRUST FUND

Proposal for Oil Trust Fund

- As of May 21, 2004, estimated crude oil export revenue reached $6.2 billion for 2004 (crude oil export revenue for 2003 [June - December] was $5.1 billion).

IV.  LAY FOUNDATIONS FOR AN OPEN ECONOMY

Provide IG Staff Capability; Trade Bank; WTO Observer Status; Develop Framework for Collateralizing Movable and Immovable Property

- Since opening in December 2003, the Trade Bank of Iraq has opened 206 letters of credit totaling $789.01 million, financing imports from thirty-three countries.  Included is one letter of credit guaranteed by the Export-Import Bank of the United States for $6.9 million, nineteen letters of credit for a total of $26.2 million pending issuance, and twenty-three letters of credit to be funded with Oil for Food funds pending issuance.

- A management information system (MIS) for tracking micro-credit loans was provided for both CPA microfinance institutions partners, CHF and ACDI/VOCA.  This MIS was provided by USAID through Bearing Point as part of the technical assistance and training provided to theses microfinance institutions.  The system generates timely financial statements, which adhere to international accounting and financial standards and will monitor progress and impact as the program expands

- The first microfinance loan has been made in Falluja -- $1,500 to an auditor to buy a car for business travel.  More will follow, as microfinance lender and CPA grantee, Al Thiqa, establishes a presence in Al Anbar Province.

- The non-profit Small Business Loan Committee (SBLC) in Mosul will expand its operations with the purchase of office equipment and supplies.  The SBLC has delivered more than 200 micro-credit loans to local businesses and individuals in the Ninewa province.

- A Ministry of Trade delegation attended the World Trade Organization General Council meeting May 17 – 18, 2004 in Geneva Switzerland.  This was the first formal participation in the WTO by Iraq since receiving its Observer status earlier this year.  The Iraqi delegation organized and attended a separate series of meetings with other member governments, and the professional Secretariat of both the WTO and the World Intellectual Property Organization.    The subjects of these meetings were how best to assist the re-integration of Iraq into the world trade economy.

V.  PURSUE NATIONAL STRATEGY FOR HUMAN RESOURCES DEVELOPMENT

Begin to employ workers in Public Works programs around the country

- Ongoing security problems are still creating gaps in employment reporting.  Multinational Forces Iraq (MNF-I) Civil Affairs units estimate that the CPA has created 435,809 jobs for Iraqi citizens (51 percent of the MNF-I target of 850,000):

    - Security/national defense employs:			           248,391

    - National / regional jobs programs employ:                     	             44,031

    - CJTF-7 employs:              						 54,738

    - Civilian contractors employ:					 87,099

      - Employed through PMO-related contracts		 25,654

    - Governorate teams employ:                     			               1,550